## Sheet1
Story Point Estimates
Stories | 1 Point | 2 Points | 3 Points | 5 Points | 8 Points | 13 Points | 21 Points
| 168 Lab 1 | 268 Timing Lab 8 | 268 Lab 3 Stack Testing | 268 Lab 1 Board Games | 268 Lab 7 Maze | 448 Project 1 | 448 Project 2
| 368 Assignment 1 | 268 Recursion Lab 6 | 368 Pie Chart | 268 Linked List Lab | 368 Nin Game | 368 Assignment 7
| 168 Lab 2 | 368 Assignment 2 | 168 Lab 6 Input Output | 268 Lab 4 Elevator | 168 Lab 11 DMV | 268 Pokemon Lab
1 Story Point = 1 hour
Project 3 estimated to be a 13 point story
Estimate for project 3 is based on the estimates for 13 point assignments
We expect project 3 to take a similar amount of time to project 1, but not quite as much as Project 2 since we are just making the prototype right now.
Code writing will take up most of our time. Probably around 8 hrs
We need to create an interface to store quizzes
Create at least one quiz
Commenting and Documentation. Probably around 2 hrs
Then Testing and Code Review. Probably around 1 hr
Meetings. Probably around 2 hr